## Calculator
Sprint | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Schedule Variance (SV) = EV - PV | Cost Variance (CV) = EV - AC | Schedule Performance Index (SPI) = EV / PV | Cost Performance Index (CPI) = EV / AC
Sprint 1 | 10 | 15 | 9 | 5 | 6 | 1.5 | 1.6667
Sprint 2 | 10 | 15 | 9 | 5 | 6 | 1.5 | 1.6667
Sprint 3 | 10 | 15 | 9 | 5 | 6 | 1.5 | 1.6667
Totals | 30 | 45 | 27 | 15 | 18 | 1.5 | 1.6667

## Instructions
Instructions
Agile EVM Calculator for 3 Sprints
How to use:
1) On the Calculator sheet, enter PV, EV, and AC for Sprint 1–3.
2) The template auto-calculates SV, CV, SPI, and CPI per sprint.
3) The Totals row shows cumulative PV, EV, AC and overall SV, CV, SPI, CPI.
4) SPI < 1.0 indicates schedule slippage. CPI < 1.0 indicates cost inefficiency.
5) Optional: Create charts from PV, EV, AC to build burnup visuals.
Notes:
- PV (Planned Value) is the budgeted value of planned work.
- EV (Earned Value) is the budgeted value of completed work.
- AC (Actual Cost) is what you actually spent.