## RACI
Activity / Person | Person1 | Person2 | Person3 | Person4
Approvals | R | A | A
Inspections | CI | R | I
Renovation | C | A | I | R
Purchase | C | CI | R
R -Responsible
A - Accountable
C - Consulted
I - Informed

## Cost Estimate
Resource | Cost | Units | Subtotal | Type
Mover | $75/h | 6 | 270 | T&M
Labor | 500 | 1 | 500 | Fixed
Cost of boxes | 3 | 100 | 300 | Fixed
Mis cost | 200 | 1 | 200 | Fixed
Inspection | 750 | 1 | 750 | Fixed
Repairs | 120 | 16 | 1920 | T&M
Gov Fees | 450 | 1 | 450 | Fixed
|  | Total | 4390

## Resources
Required
Mover | 3
Labour | 1
Procurment | 1
Inspector | 1
Handyman | 2

## CP
Stakeholder | Document | Format | Contact | Frequency
Labor | 3 days notice | phone call | Mr. Friend | 1 time
Labor | 1 day notice | phone call | Mr. Friend | 1 time
Inspector | Sing contract | email | Mr. Inspector | 1 time
Inspector | 1 day confirmation | phone call | Mr. Inspector | 1 time
Handyman | Sing contract | email | Mr. Contractor | 1 time
Handyman | 1 day confirmation | phone call | Mr. Contractor | 1 time
Mover | 3 days notice | text msg | Mr. Mover | 1 time
Mover | 1 day notice | phone call | Mr. Mover | 1 time

## RR
ID | Description of risk | Impact | Risk Resonce | Risk Level | Risk Owner | Notes | Qualitative | Probability | Cost | value | Responses
1 | Inspector avilability | No inspection | Alternative inspector | Low | Owner |  | Proximity | 0.05 | 500 | 25 | Mitigate
2 | Contractor avilability | Repairs are not done | Alternative contracor | Low | Owner |  | Proximity | 0.4 | 10000 | 4000 | Accept
3 | Mover avilability | Delay in moving | Notify 3 days | Medium | Owner |  | Urgency | 0.1 | 5000 | 500 | Mitigate
0
0
0

## QA
Item | Description | Status
1 | Kitchen packed | in progress
2 | Fragile items bubble wrapped | done
3 | Moving contractor is a business not an individual | in progress
4 | Keep cost recipes for tax | in progress
5 | a. Prepare check list based on inspection document | in progress
6 | Inspect the repairs | in progress
7 | Check all items are completed to our satisfaction | in progress
8 | Verify there are no damages | in progress
9 | Verify construction waste is removed | in progress

## SE
Stakeholder | Unaware | Resistant | Neutral | Supportive | Leading
Nick |  | C |  |  | D
Bob | C |  |  |  | D
Jane |  |  |  | CD
C - current level of engagement
D - desired level of engagement